## Project Planner
S Durbridge Independent Engineering Scholarship 2017
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS |  |  | 1 Week Blocks Divided into 2 2hour sessions [bare minimum work] 16 weeks in total
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
Generic FDTD Algorithm Development 1D | 1 | 2 | 1 | 2 | 50%
Generic FDTD Algorithm Development 2D | 2 | 2 | 1 | 2 | 50%
Generic FDTD Algorithm Development 3D | 3 | 2 | 1 | 2 | 50%
Sparse FDTD Algorithm Development 1D | 4 | 2 | 1 | 0 | 10%
Sparse FDTD Algorithm Development 2D | 6 | 2 | 1 | 0 | 10%
Sparse FDTD Algorithm Development 3D | 7 | 2 | 1 | 0 | 10%
Test SparseFDTD algorithm for speed | 8 | 1 | 0 | 0 | 0%
PTSD Algorithm Development 1D | 9 | 2 | 1 | 2 | 50%
PTSD Algorithm Development 2D | 10 | 2 | 1 | 2 | 25%
PTSD Algorithm Development 3D | 11 | 2 | 1 | 2 | 25%
Test PTSD Algorithm for speed | 12 | 1 | 0 | 0 | 0%
Develop domain handling code | 13 | 2 | 0 | 0 | 0%
Calculate domain response using IM and hand calculated | 15 | 1 | 0 | 0 | 0%
Round 1 Comparitive Testing & Accuracy Confirmation | 16 | 1 | 0 | 0 | 0%
SFDTD Refinement 1 | 17 | 1 | 0 | 0 | 0%
PTSD Refinement 1 | 18 | 1 | 0 | 0 | 0%
FDTD Refinement 1 | 19 | 1 | 0 | 0 | 0%
Round 2 Comparitive Testing & Accuracy Confirmation | 20 | 1 | 0 | 0 | 0%
SFDTD Profiling & Code Refinement | 21 | 1 | 0 | 0 | 0%
PTSD Profiling & Code Refinement | 22 | 1 | 0 | 0 | 0%
Round 3 Comparative Testin & Accuracy Confirmation | 23 | 1 | 0 | 0 | 0%
SFDTD GPU Config | 24 | 1 | 0 | 0 | 0%
PTSD GPU Config | 25 | 1 | 0 | 0 | 0%
FDTD GPU Config | 26 | 1 | 0 | 0 | 0%
Round 4 Comparative Testin & Accuracy Confirmation | 27 | 1 | 0 | 0 | 0%
Develop Matlab UI | 1 | 28 | 1 | 0 | 10%
Report Writing: Problem Intro | 1 | 2 | 0 | 0 | 0%
Report Writing: FDTD Description | 4 | 2 | 0 | 0 | 0%
Report Writing: SFDTD Description | 8 | 2 | 0 | 0 | 0%
Report Writing: PTSD Description | 12 | 2 | 0 | 0 | 0%
Report Writing: Domain & Testing Description | 14 | 2 | 0 | 0 | 0%
Report Writing: Generating results to confirm model Accuracy [BEM, IMS & Analytic] | 16 | 2 | 0 | 0 | 0%
Report Writing: Confirming the Models Accuracy | 17 | 2 | 0 | 0 | 0%
Report Writing: Benchmarking 1 | 19 | 2 | 0 | 0 | 0%
Report Writing: Benchmarking 2 Optimisation 1 [REFINEMENT] | 21 | 2 | 0 | 0 | 0%
Report Writing: Benchmarking 3 Optimisation 2 [GPU] | 25 | 2 | 0 | 0 | 0%
Report Writing: Evaluation & Conclusion | 26 | 4 | 0 | 0 | 0%
Report Writing: Intro, Abstract & Error checking | 23 | 12 | 0 | 0 | 0%